## AI Factory RCM
Ref # | Component | Sub-Component / Detail | Risk Category | Risk Description | Risk Rating (H/M/L) | Control Description | Control Type (Preventive / Detective) | Control Owner | Test Procedure
AF-01 | Cloud Deployment | Azure – West Europe, Singapore, UK South | Infrastructure / Availability | Misconfiguration of Azure resources (NSGs, storage accounts, IAM roles) could expose AI Factory workloads to unauthorised access or data leakage across regions. | H | Azure Policy / Defender for Cloud enforces baseline configurations; region-specific NSG rules restrict east-west traffic; quarterly CIS benchmark scans with remediation SLAs. | Preventive / Detective | Cloud Ops / ICS | Obtain Azure Policy compliance dashboard; sample 10 resources per region and verify CIS benchmark alignment; review Defender for Cloud alerts and remediation evidence for the last quarter.
AF-02 | Cloud Deployment | Azure – Multi-region | Data Residency / Regulatory | Hosting in West Europe, Singapore and UK South introduces cross-border data transfer risks and potential non-compliance with local data protection regulations (GDPR, PDPA, UK DPA). | H | Data classification labels enforced at storage layer; Azure Private Endpoints prevent public egress; data residency controls validated during Landing Zone deployment. | Preventive | Data Privacy / Legal | Review data flow diagrams for each region; verify no cross-region replication of restricted data; inspect Private Endpoint configurations and confirm compliance with DPIA requirements.
AF-03 | Cloud Deployment | Azure – Multi-region | Business Continuity | Single-region outage could disrupt AI Factory services if failover mechanisms are not tested or documented. | M | Multi-region deployment with Azure Availability Zones; BCP/DR runbooks documented and tested annually; RTO/RPO defined per workload tier. | Preventive / Detective | Cloud Ops | Obtain BCP/DR test results; verify RTO/RPO targets are met; review Azure Service Health alert configurations and incident response playbooks.
AF-04 | LLM Endpoints | Programmatic access to production LLM endpoints | Unauthorised Access | Inadequate authentication or authorisation on LLM API endpoints may allow unauthorised consumers to invoke models, leading to data exposure or cost overruns. | H | API Gateway enforces OAuth 2.0 / mTLS authentication; RBAC limits endpoint access to approved consumer applications; API rate limiting and usage quotas configured per consumer. | Preventive | Platform Engineering | Review API Gateway auth configuration; test with invalid/expired tokens to confirm rejection; verify RBAC role assignments against approved consumer list; inspect rate-limit thresholds.
AF-05 | LLM Endpoints | Programmatic access to production LLM endpoints | Availability / Performance | Uncontrolled or bursty API consumption could exhaust endpoint capacity, degrading service for other consumers. | M | Per-consumer rate limiting and throttling policies; auto-scaling configured on Databricks Model Serving endpoints; monitoring dashboards with alerting on latency / error rate thresholds. | Preventive / Detective | Platform Engineering | Review rate-limit and throttling configurations; simulate burst traffic in non-prod and confirm throttling triggers; verify auto-scaling policies and alert thresholds.
AF-06 | Models Available (R1) | Llama 3.3 70B, Claude Sonnet 3.7, BGE-Large-EN, GPT-4o | Model Risk / Bias | Commercial and open-source models may produce biased, inaccurate, or hallucinated outputs that could lead to incorrect business decisions if consumed without validation. | H | AI Guardrails layer (MS AI Content Safety + Presidio) screens outputs; model evaluation benchmarks run pre-deployment; model cards documenting known limitations shared with consumers. | Preventive / Detective | AI/ML CoE | Obtain model evaluation reports and benchmark results; review model cards for documented limitations; test sample prompts and assess output quality against acceptance criteria.
AF-07 | Models Available (R1) | Llama 3.3 70B, Claude Sonnet 3.7, BGE-Large-EN, GPT-4o | Third-Party / Vendor | Dependency on multiple third-party model providers (Meta, Anthropic, Databricks, OpenAI) creates vendor concentration and contractual/licensing risk. | M | Vendor risk assessments completed per SCB TPSA framework; contractual SLAs and data processing agreements in place; exit strategy documented for each model provider. | Preventive | Vendor Management / ICS | Verify TPSA assessments are current for each vendor; review contractual SLAs, data processing terms, and IP/licensing clauses; confirm exit strategy documentation.
AF-08 | Models Available (R1) | Open-source: Llama 3.3 70B | IP / Licensing | Use of open-source models (Meta Llama) without adherence to licence terms (e.g., Meta Community Licence) could expose the bank to legal or IP risks. | M | Legal review of all OSS model licences prior to onboarding; licence compliance checklist maintained; usage monitoring to ensure terms are met (e.g., user thresholds). | Preventive | Legal / AI CoE | Obtain legal sign-off for each OSS licence; review compliance checklist; verify user counts against licence thresholds.
AF-09 | AI Guardrails | MS AI Content Safety + Presidio | Content Safety | Insufficient or misconfigured content moderation could allow harmful, offensive, or non-compliant content to pass through LLM outputs to end users. | H | Microsoft AI Content Safety filters configured for hate, violence, self-harm, sexual content categories at appropriate severity thresholds; regular red-team testing of filter effectiveness. | Preventive / Detective | AI/ML CoE / ICS | Review AI Content Safety severity thresholds and filter configurations; conduct red-team prompt injection / jailbreak tests (OWASP LLM Top 10 aligned); verify alert/block logs.
AF-10 | AI Guardrails | Presidio – PII Detection | Data Leakage / Privacy | LLM prompts or responses may inadvertently contain PII/sensitive data; failure to detect and redact this data creates privacy and regulatory breach risk. | H | Presidio PII detection integrated into prompt input and output pipelines; custom recognisers configured for SCB-specific data patterns (account numbers, SWIFT codes); detection accuracy monitored. | Preventive / Detective | Data Privacy / AI CoE | Test Presidio with sample PII-laden prompts covering SCB data types; verify redaction accuracy; review false-positive/negative rates; confirm custom recogniser configurations.
AF-11 | Pipeline Support | Lifecycle mgmt for isolated LLM endpoints | Change Management | Inadequate lifecycle controls for creating, updating, or decommissioning LLM endpoints may lead to orphaned or misconfigured endpoints in production. | M | Endpoint provisioning follows change management process with approval workflows; endpoint inventory maintained with ownership and status tracking; periodic reconciliation of active endpoints. | Preventive / Detective | Platform Engineering | Review endpoint provisioning change records; reconcile active endpoints against inventory; verify decommissioning evidence for retired endpoints.
AF-12 | Integration | Compatible with SC-IDP | Identity & Access | Misalignment with SC-IDP identity federation could allow access bypass or create orphan accounts with elevated privileges. | H | Integration with SC-IDP for SSO and identity federation; access provisioning via automated JML (Joiner-Mover-Leaver) workflows; periodic access recertification. | Preventive / Detective | IAM / Platform Engineering | Verify SC-IDP integration config (SAML/OIDC settings); test SSO flow; review JML process evidence; sample 20 accounts and verify access recertification completion.
AF-13 | Databricks Workspace | Collaborative data workspaces – no structured data ingestion in R1 | Unauthorised Access | Overly permissive workspace access could allow users to view, modify, or exfiltrate data or code belonging to other teams. | H | Workspace-level RBAC enforced via Unity Catalog; network isolation between workspaces; access limited to authorised users via SC-IDP integration; no structured data ingestion in R1 reduces exposure. | Preventive | Platform Engineering | Review workspace access lists and RBAC role assignments; verify network isolation controls; confirm no structured data has been ingested; test cross-workspace access restrictions.
AF-14 | Databricks Workspace | Collaborative data workspaces | Code Security | Notebooks and scripts in shared workspaces may contain hardcoded secrets, API keys, or sensitive configurations. | M | Secret management via Databricks Secrets / Azure Key Vault integration; automated secret scanning on notebook commits; developer guidance on secure coding practices. | Preventive / Detective | Platform Engineering / ICS | Run secret scanning tool against sample notebooks; verify Key Vault integration and secret rotation policies; review developer guidance documentation.
AF-15 | Unity Catalog | Data access control – no structured data ingestion (EDMP not available) | Data Access Control | Misconfigured Unity Catalog permissions could grant excessive access to embedding data or allow cross-workspace data access. | H | Unity Catalog enforces three-level namespace (catalog.schema.table) access control; workspace users limited to their own embedding data; access policies reviewed quarterly. | Preventive / Detective | Data Platform / ICS | Review Unity Catalog permission grants; verify users can only access their own embedding data; test cross-workspace access attempts; review quarterly access review evidence.
AF-16 | Unity Catalog | No EDMP integration yet | Data Governance | Absence of EDMP integration means data lineage, classification, and cataloguing capabilities are limited, reducing visibility into data provenance. | M | Manual data inventory maintained for R1; data classification applied at workspace level; EDMP integration planned for subsequent release with migration controls. | Detective | Data Governance | Review manual data inventory completeness; verify classification labels on stored embedding data; confirm EDMP integration roadmap and timeline.
AF-17 | RAG (FileNet) | RAG pipelines sourcing documents from FileNet | Data Leakage | RAG pipelines may retrieve and surface sensitive or classified documents from FileNet without adequate access enforcement, leading to unauthorised information disclosure. | H | FileNet document-level ACLs propagated to RAG retrieval layer; embedding storage access scoped per workspace; output filtered through Presidio PII detection before delivery to users. | Preventive / Detective | AI CoE / Data Platform | Map RAG retrieval pipeline end-to-end; verify FileNet ACL enforcement at retrieval; test with restricted documents to confirm access denial; review Presidio filtering on RAG outputs.
AF-18 | RAG (FileNet) | Document ingestion and chunking | Data Integrity | Incorrect document chunking, parsing errors, or stale embeddings could lead to inaccurate or misleading retrieval results. | M | Chunking strategy documented and validated; embedding refresh schedules defined; retrieval accuracy metrics monitored; human-in-the-loop validation for critical use cases. | Detective | AI CoE | Review chunking strategy documentation; verify embedding refresh frequency; test retrieval accuracy with known document sets; review monitoring dashboards and accuracy metrics.
AF-19 | Quarantine Zone | Secure isolation for open-source models (Hugging Face) | Malicious Code / Supply Chain | Open-source models downloaded from public repositories (Hugging Face) may contain malicious code, backdoors, or poisoned weights that could compromise AI Factory integrity. | H | All OSS models must pass through Quarantine Zone before production use; automated malware and vulnerability scanning; model integrity verification (hash checks, signature validation); manual security review for high-risk models. | Preventive / Detective | Security Ops / AI CoE | Review Quarantine Zone scanning logs; verify hash/signature checks against published model digests; test quarantine workflow with a sample model download; review manual review sign-off records.
AF-20 | Quarantine Zone | Model validation pipeline | Compliance | Insufficient validation criteria or bypassing the quarantine process could allow non-compliant or untested models into production. | H | Quarantine exit gate with mandatory checklist (security scan pass, licence review, bias evaluation, performance benchmarks); workflow enforces sequential gates with no bypass option. | Preventive | AI CoE / Compliance | Obtain quarantine exit checklist; verify all gate criteria are documented and enforced; sample 3 recently onboarded models and trace through quarantine workflow; confirm no bypass evidence.
AF-21 | AI/ML/LLMOps | Code deployment only – no model training in R1 | Change Management | Inadequate CI/CD controls for code deployment to LLM endpoints could introduce untested or vulnerable code into production. | M | CI/CD pipeline with mandatory code review, automated testing, SAST/DAST scanning, and approval gates before production deployment; deployment logs maintained. | Preventive / Detective | DevOps / Platform Engineering | Review CI/CD pipeline configuration; verify mandatory approval gates; sample 5 recent deployments and trace through pipeline stages; review SAST/DAST scan results.
AF-22 | MLFlow | Model versioning and registration in Databricks | Model Governance | Lack of proper model versioning and registration could lead to untracked model changes, making it difficult to reproduce results or roll back to previous versions. | M | MLFlow enforced as mandatory registration service; model versions tracked with metadata (owner, date, lineage, performance metrics); production promotion requires explicit approval. | Preventive / Detective | AI/ML CoE | Review MLFlow registry for completeness of metadata; verify approval workflow for production model promotion; sample 3 model versions and confirm lineage and rollback capability.
AF-23 | MLOps Pipeline | Model training and deployment for traditional ML | Model Risk | Traditional ML model training without adequate validation, bias testing, or performance monitoring could produce models that degrade over time or produce unfair outcomes. | H | Model validation framework with bias/fairness testing pre-deployment; performance monitoring with drift detection; model retraining triggers defined; MRM (Model Risk Management) review for material models. | Preventive / Detective | AI/ML CoE / MRM | Review model validation reports and bias testing results; verify drift detection alerting; confirm MRM review completion for material models; test retraining trigger mechanisms.
AF-24 | Sandbox Environment | Secure sandbox with masked production data | Data Leakage | Inadequate data masking or insufficient isolation from production could result in exposure of real customer data in the sandbox environment. | H | Data masking applied before ingestion into sandbox using approved masking algorithms; network segmentation enforces strict isolation from production; no direct connectivity to production data sources. | Preventive | Data Platform / Security | Verify data masking rules and algorithms; test masked data samples for residual PII; review network segmentation rules; confirm no production connectivity paths.
AF-25 | Sandbox Environment | Data scientist access | Privilege Escalation | Data scientists may gain excessive permissions in the sandbox that could be leveraged to access production systems or unmasked data. | M | Sandbox RBAC with least-privilege access; no admin credentials shared; access reviews conducted quarterly; sandbox credentials do not grant production access. | Preventive / Detective | IAM / Data Platform | Review sandbox RBAC assignments; verify credential isolation from production; sample user access and confirm least privilege; review quarterly access review evidence.
AF-26 | Elastic Integration | RAG with external knowledge bases | Data Leakage / Unauthorised Access | Integration with external Elastic knowledge bases could expose sensitive data if access controls are not aligned between AI Factory and the external source. | H | Federated access controls enforced; API authentication (mTLS/OAuth) required for Elastic connectivity; data classification validation at ingestion; network-level restrictions (private endpoints/VPN). | Preventive | Platform Engineering / Security | Review Elastic integration architecture and data flow; verify authentication mechanisms; test access controls alignment; confirm network restrictions and private endpoint usage.
AF-27 | Landing Zone Design | Unstructured data classification, PII detection, tokenisation | Data Classification | Failure to properly classify unstructured data at the landing zone could result in sensitive data being processed or stored without appropriate controls. | H | Automated data classification at ingestion using approved taxonomy; PII detection and tokenisation applied before data moves beyond landing zone; classification audit trail maintained. | Preventive / Detective | Data Platform / Data Privacy | Review classification taxonomy and rules engine configuration; test PII detection with sample unstructured data; verify tokenisation output; review audit trail logs.
AF-28 | Landing Zone Design | Tokenisation controls | Data Integrity | Incorrect tokenisation could corrupt data or create re-identification risk if tokenisation is reversible or poorly implemented. | M | Tokenisation uses approved irreversible algorithms for non-essential fields; reversible tokenisation (format-preserving encryption) limited to authorised use cases with key management controls. | Preventive | Data Platform / Security | Review tokenisation algorithm selection; verify key management controls for reversible tokenisation; test tokenised data for re-identification risk; review authorisation for reversible use cases.
AF-29 | SharePoint Integration | Document and knowledge management connectivity | Data Leakage | SharePoint integration could inadvertently expose confidential documents or internal knowledge assets to AI Factory workflows without proper access enforcement. | M | SharePoint permissions propagated to AI Factory access layer; document-level access controls enforced at retrieval; integration limited to approved SharePoint sites/libraries. | Preventive | Platform Engineering / Collaboration | Review SharePoint integration configuration; verify permission propagation; test retrieval of restricted documents to confirm access denial; review approved site/library list.
AF-30 | EDMP Integration | Enterprise Data Management Platform connectivity | Data Governance | Without EDMP integration (not yet available), structured data governance (lineage, quality, cataloguing) is limited, creating risk of ungoverned data flows in future releases. | M | EDMP integration roadmap defined with target release; interim manual data governance controls in place; data quality checks applied at ingestion points; governance gaps documented in risk register. | Detective | Data Governance / Data Platform | Review EDMP integration roadmap and target dates; verify interim governance controls; review risk register entries for governance gaps; confirm data quality check evidence at ingestion points.